## Current state
Sr. No. | Areas | Current State (Admin / Team) | Current State (Customer / User)
1 | Problem Understanding | Only a broad idea: “fast OTC medicine delivery.” Not yet validated with real customers. | Customers today buy OTC items either from local chemists (fast but offline) or apps like 1mg/PharmEasy (convenient but slow).
2 | Value Proposition | Defined loosely as “Blinkit + 1mg.” Not yet sharpened (speed vs price vs reliability). | Users don’t clearly see what is different or why to switch.
3 | Target Customers | No confirmed user segments (working professionals, parents, elderly). | Each group has different needs (speed, convenience, trust).
4 | Market Research | No deep study of competitors, regulations, or demand in one city. | Users are used to strong brands (PharmEasy, Apollo, Blinkit).
5 | Compliance & Licensing | Assumes OTC-only avoids legal issues; no clarity on required pharmacy tie-ups or licenses. | Customers expect safety and legal products.
6 | Pharmacy Partnerships | No agreements yet; unclear if pharmacies can/will update inventory. | Customers risk ordering items that are unavailable.
7 | Inventory Management | No system yet for “live stock.” Unsure if pharmacies have POS systems to connect. | Users don’t get accurate stock visibility today.
8 | Delivery Operations | No delivery model chosen (own fleet vs 3PL like Dunzo/Shadowfax). | Customers expect <1hr delivery like Swiggy/Zomato.
9 | Product Catalog | No curated OTC product list yet (basic items like painkillers, wellness, baby care). | Customers see unstructured catalogs elsewhere; often hard to find essentials quickly.
10 | Payments & Pricing | No integration with payment gateway yet. No plan for commission vs margin model. | Customers often pay offline; want UPI/COD with refunds.
11 | Customer App | No design or build started. Only high-level idea (Android + profiles). | No single app exists for instant OTC delivery with live tracking.
12 | Pharmacy/Partner Portal | No portal yet. Unsure if web or mobile app will be first. | Customers don’t see which pharmacy is fulfilling their order.
13 | Admin Panel | No system yet to track orders, payments, or catalog. Ops would be manual. | Customers won’t get timely updates or support without it.
14 | Technology Readiness | No chosen tech stack, hosting, or integration plan. 8–10 week build is aggressive. | Customers expect Blinkit-level smoothness from day 1.
15 | Go-To-Market Plan | No launch city decided. No waitlist, no pilot test defined. | Customers don’t know about the service; adoption risk.
16 | Operations & Support | No defined SOPs for order issues (substitutions, refunds, delays). | Customers will be frustrated if problems aren’t handled clearly.
17 | Metrics & Success Criteria | No clear MVP KPIs yet (delivery SLA, fill rate, NPS, AOV). | Customers’ trust and adoption can’t be measured without them.
18 | Team & Resources | Small founder team or unclear roles for tech, ops, and pharmacy partnerships. | Customers will get poor support if there’s no dedicated team.
19 | Scalability & Growth | Only MVP in mind & no long-term plan for iOS app, advanced analytics, or loyalty programs. | Customers expect continuous improvements (offers, rewards, faster UX).

## Questionnaire
Questionnaire
Sr. no. | Category | Discussion Questions
1 | Vision & Mission | When you think about this app, what is its core mission? Is it primarily about making OTC medicines more convenient to access, about offering affordability, or about increasing accessibility for underserved users?
2 |  | Beyond immediate business goals, how do you envision this platform making a long-term positive impact on the healthcare retail ecosystem in India?
3 | Market Need | From your perspective, what specific pain points are customers facing today that current players like Blinkit, 1mg, or Apollo have not fully solved — and how will we address them better?
4 |  | Who do you see as our primary target users in Phase 1 — is it urban youth who want instant access, families managing daily needs, or elderly customers who require trust and reliability?
5 | Market Size | Have you thought about the TAM (Total Addressable Market) and SAM (Serviceable Available Market) for this sector, and where our opportunity lies within that?
6 |  | Which geography or city do you believe would be the best place to run our pilot rollout, and what makes that location strategically important?
7 | Competitive Positioning | In terms of competitive differentiation, do you believe our edge should be speed of delivery, pricing, product range, reliability and trust, or an overall superior customer experience?
8 | Product Strategy | Should the initial version of the app focus only on OTC medicines, or would it make sense to include wellness, personal care, and related health products from the start?
9 |  | At launch, what proportion of our catalog (SKUs) should ideally be enabled with live inventory tracking to give customers a reliable experience?
10 | Delivery Model | At launch, what proportion of our catalog (SKUs) should ideally be enabled with live inventory tracking to give customers a reliable experience?
11 |  | What is the realistic and desirable average delivery time in the first phase — 30 minutes, 1 hour, or same-day fulfillment — given our resources and customer expectations?
12 | Revenue Model | For revenue in the early stage, should we rely more on pharmacy margins, delivery fees, subscription plans, ads, or a hybrid model — and why?
13 |  | From a financial standpoint, what gross margin percentage do you believe is realistic to target in the first 6–12 months while balancing growth and sustainability?
14 | Inventory & Tech | How do you imagine live inventory should be technically implemented — through direct POS integration with pharmacies, manual stock updates, or APIs in the first phase?
15 |  | Do you think pharmacies will readily share their real-time inventory data, or would we need to provide incentives/benefits for them to adopt the system?
16 | User Experience | From a user perspective, what should be the three most important features at launch — for example, advanced search, easy reordering, prescription upload, or digital payments?
17 |  | Should the platform include multilingual support from the beginning to ensure inclusivity across different customer segments, or should that come later?
18 | Compliance | What are the key legal and regulatory requirements (such as pharmacy licenses, GST, or OTC drug compliance) that we must resolve before launch?
19 |  | Are there any categories of OTC products or health items that we legally cannot sell online, and how do we handle those restrictions?
20 | Partnerships | What approach do you see as most effective to onboard pharmacy partners — direct contracts, working through aggregators, or manual enrollment in Phase 1?
21 |  | In your view, what commission rate or incentive structure will be acceptable to pharmacies so that they are motivated to work with us during the early stages?
22 | Marketing & Growth | What is our customer acquisition strategy for the first 3 months — should we focus on digital ads, local partnerships, word-of-mouth, or referral programs to create initial traction?
23 |  | What would you consider a realistic and ambitious target for active users within the first 90 days of launch, and how do we measure success at that stage?
24 | Finance & Budget | How do you believe our budget allocation should be split across technology development, operations, marketing, delivery, and compliance during the first year?
25 |  | Do you think we should prioritize reaching break-even within 12–18 months, or would it be more strategic to focus purely on growth and market share first?
26 | Risks & Difficulties | From your perspective, what are the biggest risks or challenges — regulatory hurdles, reluctance from pharmacies, customer trust, or limited funding runway?
27 |  | In case of order failures (for example, an item being unavailable after checkout), what is the best way to manage customer expectations and maintain trust?
28 | Long-Term Opportunities | Could this business eventually expand into a B2B pharmacy supply chain model, serving hospitals and clinics as well as individual customers?
29 |  | Do you see value in eventually integrating telemedicine services or doctor consultations into the platform to expand beyond retail?
30 |  | In your long-term vision, where should this startup be in 5 years — India’s leading OTC delivery app, or a more comprehensive digital healthtech platform?

## PreWork
Business Case
To develop and launch a SaaS-enabled OTC medicine delivery platform that bridges the gap between offline chemist convenience (fast but limited reach) and existing online players (wide reach but slower delivery). The goal is to provide a fast, reliable, and transparent OTC medicine delivery service, integrated with local pharmacy inventory and offering a seamless mobile-first user experience.
Sr. No. | Problem Area | Challenges | Description | Initial Assumptions | Proposed Success Criteria (KPIs)
1 | Problem Understanding | Idea not validated | Customers rely on either offline chemists (fast but offline) or apps like 1mg/PharmEasy (convenient but slow). | Customers need faster OTC delivery than current apps provide. | Validate demand via 50+ customer interviews; measure interest using survey score >70%.
2 | Value Proposition | Loosely defined as “Blinkit + 1mg” | Customers don’t see why to switch. | Customers will pay for speed + reliability. | MVP NPS ≥ 60; % of users willing to pay for faster delivery ≥ 50%.
3 | Target Customers | No segmentation | Different needs: speed, trust, affordability. | Urban millennials and working professionals are primary users. | At least 2 customer personas validated; segment adoption ≥ 50% in pilot city.
4 | Market Research | No deep study | Users are used to strong brands like Apollo, PharmEasy. | Competitors have service gaps in speed and availability. | Competitive gap analysis completed; at least 1 unique differentiator validated.
5 | Compliance & Licensing | No clarity | Customers expect safety, legal compliance. | Pharmacy partners will comply with legal requirements. | All pharmacy partners onboarded with valid licenses; zero compliance incidents in pilot.
6 | Pharmacy Partnerships | No agreements | Risk of unavailable items for customers. | 10–15 local pharmacies can supply essential OTC products. | ≥80% of items in MVP catalog are available in stock daily.
7 | Inventory Management | No live stock system | Customers can’t see accurate availability. | Inventory can be updated daily via POS integration or manual input. | Stock accuracy ≥ 95%; out-of-stock incidents < 5% per week.
8 | Delivery Operations | No delivery model | Customers expect <1hr delivery like Zomato/Swiggy. | 3PL/own fleet can deliver within 60 mins in pilot city. | On-time delivery ≥ 90%; avg. delivery time ≤ 60 mins.
9 | Product Catalog | No curated OTC catalog | Customers find essentials hard to locate quickly. | Top 100 essential OTC products cover ≥80% demand. | Catalog ready with 100 products; 90% orders fulfilled from catalog.
10 | Payments & Pricing | No gateway/model | Customers prefer UPI/COD with refunds. | Users will adopt UPI/COD; refund process manageable. | Payment success rate ≥ 98%; refund SLA ≤ 24 hours.
11 | Technology Readiness | No tech stack | Customers expect Blinkit-level smoothness. | MVP can be built on minimal tech stack within 3 months. | App uptime ≥ 99%; crash rate <1% in pilot.
12 | Go-To-Market Plan | No launch plan | Customers don’t know the service exists. | Launch in 1 city with limited marketing can validate demand. | Pilot city waitlist ≥ 500 users; 2-week trial adoption ≥ 60%.
0

## MVP Feature list
Core MVP Features
Sr. No. | Feature List |  | Rationale | Practical Implementation Alternative (Core MVP)
| Admin User | Application User
1 | Pharmacy Management Portal | NA | Critical for partner operational efficiency and onboarding. | Simple web login for partners to view orders, update stock, confirm readiness.
2 | Central Admin Dashboard | NA | Essential for ops, support, and monitoring business health. | View all orders, handle issues (refunds, substitutions), monitor inventory.
3 | Automated Commission Engine | NA | Automates the most critical financial operation with partners. | System calculates margin per order and generates weekly payout reports.
4 | Manual Order/Inventory Override | NA | Necessary for handling edge cases and system failures. | Admins can manually create orders or adjust inventory to resolve issues.
5 | Customer & Order Search | NA | Empowers support teams to resolve queries quickly. | Search for users by phone number or order ID to view status and history.
6 | Simple Analytics Dashboard | NA | Data-driven decision making is non-negotiable. | Google Data Studio to track Order Volume, AOV, Delivery Time, Cancel Rate.
7 | NA | OTC-Centric Smart Catalog | 80% of orders focus on 100 essential OTC products. Curated lists build trust. | Curate essentials: pain relief, digestive health, first aid, baby care, vitamins.
8 | NA | AI-Powered Search & Voice Ordering | Voice/search is standard. Users expect intuitive, error-forgiving discovery. | Integrate a lightweight NLP API. Enable "reorder via voice" with GA/Alexa.
9 | NA | Pseudo-Live Inventory Status | Manages expectations without complex, real-time POS integration. | Manual stock updates 2x daily. Display "In Stock" / "Low Stock" / "Out of Stock".
10 | NA | Simplified, One-Page Checkout | Reduces cart abandonment. Streamlined UX is critical for adoption. | Address auto-detect, preset delivery slots, minimal fields.
11 | NA | Multi-Payment Gateway (UPI-focused) | Maximizes conversion by catering to all Indian digital payment preferences. | Integrate Razorpay/Paytm for UPI, Cards, Net Banking, and COD.
12 | NA | Basic Order Tracking (3-Step) | Manages expectations without complex, expensive live GPS maps. | Status: "Order Confirmed," "Out for Delivery," "Delivered" with SMS/App alerts.
13 | NA | Carbon-Neutral Delivery Option | A key differentiator for eco-conscious urban users. (Sustainability) | Partner with a 3PL. Add a small optional fee at checkout to offset emissions.
14 | NA | UPI-Based Referral & Rewards | Leverages India's payment network for seamless, viral growth. | Share UPI link; both get instant credit upon friend's first order completion.
15 | NA | "Digital Shelf" for Pharmacy | Builds transparency and local trust by showing who fulfills the order. | Display fulfilling pharmacy's name, logo, and rating on the product/order page.
Deferred Features (Post-MVP)
Sr. No. | Feature List |  | Rationale | Practical Implementation Alternative (Deferred)
| Admin User | Application User
1 | NA | iOS Application | Higher development cost and longer timeline (~30% of Indian market). | Launch with Android only (covers 70-75% of users). Use a cross-platform framework plan for later.
2 | NA | Live GPS Tracking | Complex integration with delivery partners; higher cost. | Provide delivery partner's name and phone number with an ETA.
3 | NA | Prescription Handling & Upload | Significant regulatory complexity and verification overhead. | Strictly focus on OTC items to avoid compliance issues.
4 | NA | Advanced Hyper-Personalization | Requires vast amounts of user data to train effective AI models. (AI/ML) | Use simple rules-based logic: "Frequently bought together" and manual bundles.
5 | NA | Multi-language Support (Deep) | Increases development, testing, and content creation time significantly. | Launch in English and one primary local language based on the pilot city.
6 | Advanced Supply Chain Analytics | NA | Blockchain for authenticity is complex. (Transparency) | Display pharmacy license details and manually log batch numbers for audit.
7 | NA | Drone Delivery Integration Pilot | Awaiting clearer regulatory approval (DGCA) and is high-cost. (Logistics Tech) | Focus on optimizing ground fleet for sub-45-minute delivery in dense urban zones.
8 | NA | AR "Try-On"/Wellness Guides | Heavy tech for non-core offerings (e.g., sunglasses, skincare). (Immersive Tech) | Use high-quality images and detailed ingredient/usage descriptions.
9 | Predictive Replenishment Engine | NA | Complex AI-driven forecasting requires deep user behavior data. | Offer a simple calendar-based subscription: "Deliver this every 30 days."
10 | B2B Ordering Portal | NA | Completely different user flow, pricing, and value proposition. | Focus solely on validating the B2C model first.